## Sheet1
Group Project Milestone
Project Title | GameScape: Personalized Video Game Discovery and Journal
Member | Xinchen Luo, Jie Li, Xiyuan Zhang, Bowen Zhu
Due Date | Until 13/6/2025(week13)
Project Milestones |  | Week | Deadline | Task | Responsible | Progress | Notes
Milestone 1：Project Planning |  | 3 | 2025-04-21 | Form project group and assign roles | All | Completed
|  | 4 |  | Decide on project direction and concept (research APIs) |  | Completed
|  |  |  | Create project proposal (title, description, API plan, database plan, user services |  | Completed
|  | 5 |  | Discuss and refine proposal content |  | Completed
|  |  |  | Develop collaboration plan (task division, communication methods, communication tools) |  | Completed
|  | 6 |  | Create project development timeline |  | Completed
Milestone 2：Backend Setup, Frontend Design, Core Features |  | 7 | 2025-05-16 | API integration test, backend server setting | Jie Li | Completed
|  | 8 |  | implementing the user interface for game search, game detail display | Bowen Zhu | Completed
|  | 9 |  | Database schema, defined model relationships | Xiyuan Zhang | Completed
|  | 10 |  | Implement web core functionality(search, save games) overall project debugging | Xinchen Luo | Completed
|  | 11 |  | Polish UI/UX for existing pages,build frontend for new features and enhance user feedback. | Bowen Zhu
|  | 11 |  | Develop backend APIs for advanced collection features (user notes, custom ratings, play status). | Jie Li
|  | 11 |  | Extend database schema and Sequelize models for advanced collection details | Xiyuan Zhang
|  | 12 |  | Project coordination, QA, and full-stack support, ensuring smooth integration of new features. | Xinchen Luo
|  | 13 |  | Final report and demo submission | All